## Defect Report
DEFECT REPORT - E-COMMERCE WEB APPLICATION (SAUCEDEMO)
Defect ID | Test Case ID | Module | Defect Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Environment / Test Data | Reported By | Date Reported | Screenshot Reference
DEF-001 | TC_PLP_006 | Product Listing | Product images identical/incorrect for problem_user | 1. Login as problem_user 2. View Products page | Each product displays its own correct image | All 6 products display the same incorrect (dog) image | Medium | P2 | Open | problem_user / secret_sauce | Subham | 2026-09-15 | Screenshots/DEF-001_problem_user_images.png
DEF-002 | TC_E2E_003 | Performance | Noticeable page-load delay after login for performance_glitch_user | 1. Login as performance_glitch_user 2. Observe time to load Products page | Page should load within an acceptable time (~1-2 seconds) | Products page took approximately 5+ seconds to render after login | Low | P3 | Open (By Design - Demo Data) | performance_glitch_user / secret_sauce | Subham | 2026-09-15 | Screenshots/DEF-002_performance_glitch.png
DEF-003 | TC_CHECKOUT_005 | Checkout | Zip/Postal Code field lacks input format validation | 1. Go to Checkout: Your Information page 2. Enter First/Last Name 3. Enter '@' as Zip Code 4. Click 'Continue' | Non-numeric/special-character input should be rejected with a validation message | Field accepted the special character with no validation and allowed checkout to proceed | Low | P4 | Open (Won't Fix - Demo App Limitation) | standard_user / secret_sauce | Subham | 2026-09-15 | Screenshots/DEF-005_zip_validation.png
DEF-004 | TC_CART_003 | Cart | 'Remove' button on Cart page unreliable for error_user | 1. Login as error_user 2. Add a product to cart 3. Go to Cart page 4. Click 'Remove' | Item is removed from the cart and badge count decrements. | Item removal was inconsistent; badge count did not reliably update | High | P2 | Open | error_user / secret_sauce | Subham | 2026-09-15 | Screenshots/DEF-003_error_user_cart.png
DEF-005 | TC_MISC_004 | Product Listing (UI) | Product images inconsistently sized/aligned for visual_user | 1. Login as visual_user 2. Observe product image sizing on Products page | Product images render at a consistent size and alignment | Product images appeared misaligned / inconsistently sized versus standard_user view | Medium | P3 | Open | visual_user / secret_sauce | Subham | 2026-09-15 | Screenshots/DEF-004_visual_user_ui.png

## Defect Summary
DEFECT SUMMARY
Total Defects Logged | 5
Severity | Count
High | 1
Medium | 2
Low | 2