## Test Plan
SOFTWARE TEST PLAN - E-COMMERCE WEB APPLICATION (SAUCEDEMO)
Project Name | E-Commerce Web Application - Manual Testing
Application Under Test (AUT) | SauceDemo (https://www.saucedemo.com)
Document Version | 1.0
Prepared By | Subham (QA Engineer)
Date | 11-Sep-2026
Status | Approved for Execution
1. INTRODUCTION / OBJECTIVE
This Test Plan defines the scope, approach, resources, and schedule for manual testing of SauceDemo, a demo e-commerce web application. The objective is to validate that the core purchase journey (Login -> Product Listing -> Product Details -> Sorting -> Cart -> Checkout -> Order Confirmation) functions correctly, is free of critical defects, and meets expected UI/UX and functional standards before a hypothetical release.
2. SCOPE
In-Scope:
• Login module - valid/invalid credential handling, account lockout, error messaging
• Product Listing (Inventory) page - product data display, cart badge, navigation menu
• Product Details page - navigation, add/remove to cart, data consistency
• Sorting - Name (A-Z/Z-A) and Price (low-high/high-low)
• Shopping Cart - add, remove, quantity display, navigation
• Checkout - customer information form validation, order overview, tax/total calculation
• Order Confirmation - completion message, cart reset, return-to-home flow
• Cross-cutting: logout/session handling, browser back-button behaviour, UI consistency
Out-of-Scope:
• Performance/load testing beyond basic observation with performance_glitch_user
• Security penetration testing, API-level testing, and database validation
• Cross-browser and mobile responsiveness testing (executed on Chrome desktop only)
• Payment gateway integration testing (SauceDemo checkout is a simulated flow)
3. TEST STRATEGY / TYPES OF TESTING
• Smoke Testing - verify critical path (login, add to cart, checkout) is stable before deep testing
• Functional Testing - verify each feature behaves per expected business rules
• Negative Testing - invalid inputs, blank mandatory fields, invalid credentials
• Boundary Value Analysis (BVA) - field length/character boundaries (e.g. Zip/Postal Code)
• Equivalence Partitioning (EP) - valid vs invalid input classes for login and checkout forms
• UI Testing - layout, labels, alignment, and image rendering across special demo users
• Regression Testing - re-verify unaffected areas after defect fixes / repeated builds
• End-to-End (E2E) Testing - complete user journey from login through order confirmation
4. TEST ENVIRONMENT
Application URL | https://www.saucedemo.com
Browser | Google Chrome (latest stable)
Operating System | Windows 11 / 64-bit
Test Data / Users | standard_user, locked_out_user, problem_user, performance_glitch_user, error_user, visual_user ¦ Password: secret_sauce
Test Management | Microsoft Excel (Test Cases, RTM, Defect Log, Execution Report)
5. ENTRY CRITERIA
• Application build/URL is accessible and stable
• Test Cases, Test Scenarios and RTM are reviewed and approved
• Required test data (user credentials) is available
6. EXIT CRITERIA
• 100% of planned high and medium priority test cases executed
• No open Critical or High severity defects blocking the core purchase flow
• All identified defects logged with severity, priority and status in the Defect Report
• Test Execution Report reviewed and sign-off obtained
7. TEST DELIVERABLES
• Test_Plan.xlsx - this document
• Test_Scenarios.xlsx - high-level scenario list
• Test_Cases.xlsx - detailed test cases with steps, data and expected results
• RTM.xlsx - Requirement Traceability Matrix
• Defect_Report.xlsx - logged defects with severity/priority/status
• Test_Execution_Report.xlsx - execution summary with pass/fail metrics
• Screenshots/ - evidence captured during execution
8. ROLES AND RESPONSIBILITIES
Role | Name / Responsibility
QA Engineer | Subham - Test design, execution, defect logging, reporting
9. RISKS AND MITIGATION
Risk | Mitigation
Demo application may reset state/data unexpectedly | Use 'Reset App State' from menu before each test session
Special test users (problem_user, error_user) introduce intentional defects | Document as known defects; do not treat as blockers for standard_user flow
No real backend - checkout does not persist orders | Validate front-end behaviour and messaging only
10. SCHEDULE (SAMPLE)
Activity | Duration
Test Planning & Scenario/Test Case design | 1 day
Test Execution (Functional, Negative, UI, BVA/EP) | 1-2 days
Regression Testing & Defect Verification | 1 day
Reporting & Sign-off | 0.5 day